## Document Comments
Review Feedback Form
Design Review Track / Stage: - or - Document Name(s): |  |  |  | Balance Conversion Final Design
CDRL(s) Number and Version: |  |  |  | CDRL-OF-003-02.01 Rev D
Document Delivery Letter / Date: |  |  |  | CTS-MBTA-01303 / October 28, 2022
Spreadsheet Submission Date: |  |  |  | 2022-11-21
Cubic Document Number(s): |  |  |  | 1098-00315
Asana link to view comments: |  |  |  | https://app.asana.com/0/515198287232338/1202848629609900/f
Comment Number | Also Submitted As | Reviewer | Topic / Area | Reference (Document, Section or Meeting Name/Date) | Short Description | MBTA Comment | Date comment was initially logged | Cubic Response | Response Date | Status
1 | 0 | SWM, NV | ⭐Balance conversion plan - generally | CDRL-OF-003-01.01 | Balance conversion requirements deadline for first compliance is inconsistent | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22 and Compliance Matrix, 10/31/22) — Further review of Balance Conversion requirements in the Compliance Matrix is needed. Based on just a quick review, the MBTA notes the following issues: Deadline for sample report (BOS-CM-9524) should be with the final design, which is Prior to P1. It is currently listed as RSC. Requirements to develop (BOS-CM-19250) and implement (BOS-CM-19251) the balance conversion solution were parsed separately to allow for appropriate deadlines to be assigned to each but they are both listed as Prior to P1. The MBTA has been flagging issues on this area for six months now - it's a very small set of requirements that needs to be reviewed. Please dedicate the resources needed to resolve the issues. — Updated comment 08/23/22 on Compliance Matrix (08/05/22) — It's unclear why BOS-CM-3897 remains tied to Pilot 2. Further, as per "Reliance on Interoperability for Balance Conversion" (https://app.asana.com/0/767917605002993/1202045015854939/f), as of this writing, the SI has declined to enter into a Change Order to complete work on the Interoperability solution. The MBTA is particularly concerned that Cubic may not be considering appropriate sequencing of these activities. -- New comment 05/26/33 on Compliance Matrix (05/20/22) -- Please review balance conversion requirements in the Compliance Matrix. Currently, they are mapped to various deadlines for first compliance in an approach that is inconsistent and not compliant with the ARPA. Note that the design must be finalized prior to Pilot 1, the functionality must be available prior to RSC and the actual services must be provided at RSC. | 2022-05-26 |  |  | Cubic - address comment
2 | Pay CDR #65, Pay Draft PDR #88, Pay Draft PDRB #94 | Accounting | ⭐Balance conversion plan - generally | CDRL-FF-008-05.A | Liability and accounting for balances converted from AFC 1.0 | — Updated comment 11/18/22 (Balance Conversion PDR, Rev D, 10/28/22) — Please incorporate the information from Cubic's 10/11/22 comment regarding Section 2.5 into the Balance Conversion CDRL. The accounting entries depicted are ancillary to information already presented in the acceoted Settlements and Liabilities CDRL. — Updated comment 06/17/22 (Balance Conversion PDR, Rev C, 05/27/22) — Note that this comment has been submitted repeatedly for more than four years. Please add a section to the Balance Conversion CDRL that describes the appropriate accounting entries to be recorded in both the AFC 1.0 and AFC 2.0 (Cubic and MBTA) General Ledgers. Please add appropriate references to the finance documents where these decisions/processes will be described. At this point, MBTA Finance is assuming that the transactions generated by the AFC 2.0 devices/systems will be a unique sales transaction type (e.g., with a unique payment type). The mapping of these transactions to MS Dynamics and FMIS postings needs to begin as soon as possible. Note also that the CDRL reference to the Settlement & Liability Tracking document is a circular dead end (Settlement & Liability points to Balance Conversion, which points to Settlement & Liability). Please reconcile the references between the two documents. — Updated comment 01/11/22 (Balance Conversion PDR, Rev B, 12/17/21) — Please add a section to the Balance Conversion CDRL that describes the appropriate accounting entries to be recorded in both the AFC 1.0 and AFC 2.0 (Cubic and MBTA) General Ledgers. Please add appropriate references to the finance documents where these decisions/processes will be described. At this point, MBTA Finance is assuming that the transactions generated by the AFC 2.0 devices/systems will be a unique sales transaction type (e.g., with a unique payment type). The mapping of these transactions to MS Dynamics and FMIS postings needs to begin as soon as possible. Note also that the CDRL reference to the Settlement & Liability Tracking document is a circular dead end (Settlement & Liability points to Balance Conversion, which points to Settlement & Liability). Please reconcile the references between the two documents. — Updated comment 09/16/21 (Balance Conversion PDR, Rev A, 08/27/21) — Balance Conversion Preliminary Design does not include these details, though the Settlement & Liability CDRL pointed to Balance Conversion Final Design for details. Please provide further details about how the System will ensure balances from AFC 1.0 will not be double-counted. Relevant requirement 4.4.5.1.7 The SI shall provide detailed accounting of all balance conversions. [CDRL: Report on balance conversions] [CDRL: Report on balance conversions ¦ Sample report] — Updated comment 08/27/21 (Settlement and Liability) — The MBTA has received additional information from Cubic about the System's capabilities with respect to revenue recognition since the delivery of this Submittal and is continuing its review of that material to support policy decisions and configuration related to revenue recognition. MBTA will provide further guidance on accounting rules in the near future. ——- Prior Comment ——- Cubic has indicated that this will be addressed in the Balance Conversion Plan. Concern remains that balances converted from AFC 1.0 may be double counted. — Updated comment — Cubic's 12/07/20 response indicates that further discussion is required with the MBTA's Accounting Team on this matter. Please add to the agenda for an upcoming workshop with that team. — Updated — Please update the Submittal to clarify how converted balances will be "separately identifiable" describe how the system will avoid double-counting of stored value revenue that is recognized at time of sale in AFC 1.0 and recognized again at time of use in AFC 2.0. -- Updated 3/11/19 -- Cubic's 2/21/19 response indicates that a submittal will be added to the submittal schedule to cover this, but as of 3/11/19 this does not appear on the submittal schedule. -- PDR Comment -- Please include more detail in the PDR submission for how liability balances will be tracked and reported. --- CDR Comment from 04/06/18--- During the Accounting workshop on 4/5-4/6, the MBTA team explained how unused AFC 1.0 balances are not tracked in the current system as a liability. Laurie Coleman explained how this would need to change in the new System. Please describe what this will look like in the new System. | 2018-04-06 |  |  | Cubic - address comment
3 | 0 | PMO | ⭐Balance conversion plan - generally | CDRL-OF-003-01.01.B, CDRl-EF-002.06.02.E | Records of attempted and failed conversions | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — Cubic has a Balance Conversion Exceptions report that captures attempts to convert balance that failed. The ARPA & the Data Warehouse Integration specification CDRL specifies that the data used to create reports be made available to the MBTA through the data warehouse. Please confirm where in the Data Warehouse this is stored. If it is not yet stored, please update to the design to ensure this data is stored in the DW. —New Comment 06/16/22 (Data Warehouse Integration, Rev E, 06/03/22 Submittal)— The MBTA was unable to identify entities or attributes that would be associated with a balance conversion event, including failed balance conversions. Please define the entities associated with these events in a subsection of section 4 of the Data Warehouse Integration CDRL. — New comment 01/11/22 (Balance Conversion PDR, Rev B, 12/17/21) — Please describe what record is kept and what reporting is available for balance conversions attempted and cancelled or failed, and the reason for the failure, for both customer service reporting and fraud mitigation purposes. | 2022-01-11 |  |  | Cubic - address comment
4 | 0 | PMO | ⭐Balance conversion plan - generally | CDRL-TE-009-01 | Add use cases for balance conversion plan | — New comment 11/19/22 (Balance Conversion, Rev D, 10/28/22) — Please add use cases to the balance conversion CDRL. | 2018-09-26 |  |  | Cubic - address comment
5 | 0 | YK | ⭐Balance conversion plan - generally | CDRL-OF-003-01.01 | Process flows | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — The MBTA notes the following remaining concerns with the process flows: Step 10 in Figures A-1 and A-3 erroneously refer to "active unenabled" cards. Please align this with the rest of the design. Step 7 in Figure A-2 does not check whether the 2.0 media is valid for conversion. Please align with the design. Neither Figure A-1 nor A-3 check for the condition defined in "Error checking for exceeding balance limit" (https://app.asana.com/0/767917605002993/1200982139414540). Please consider adding this in. Please clarify if it is possible to include sharper images, as the process flows are a bit blurry and hard to read. If this is due to their sheer size, consider whether a separate attachment could meet this need. — New comment 06/16/22 (Balance Conversion PDR, Rev C, 05/27/22) — Please update the following items in the appendices for the process flows: A.1 Walk-In: Step 18 in section 4.1.1 is missing from appendix A flow A.2 Mail-In: The flows are missing a final step where a new card is mailed to the user. It is not clear in the flow how the user gets mailed either an enabled or an unenabled card. Above step 8 please account for balance limits: 1. If the user has a 2.0 account and the AFC 1.0 balance + existing 2.0 balance is less than $500, the value is placed in the existing account 2. If the user has a 2.0 account and the AFC 1.0 balance + existing 2.0 balance exceeds $500, a new account is created and mailed to the user. Above step 14, in the "User" row, Please add a step where the user pays the enablement fee (if applicable), and the converted balance is available for travel in the AFC 2.0 system All process flows should end with an Enablement Fee being paid (if applicable) and the user having their converted balance on the 2.0 card. | 2022-06-16 |  |  | Cubic - address comment
6 | 0 | NV | ⭐Balance conversion plan - generally | CDRL-OF-003-01.01.A | Tapping a 2.0 card instead of a 1.0 card during conversion | — Updated comment 11/17/22 (Balance Conversion, Rev D, 10/28/22) — If an old card is presented in lieu of a new card (after a valid old card has already been presented), please add an error message stating that a new card must be presented or typed in (at the mail-in flow). Please add this condition to the flows as well, clarifying if the error would abort the entire process, or if the flow would continue from screen 12A-4. Step 3 in Section 3.2 says the software will just time out, which seems like a bad UX. — Updated comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Now that the design has changed to add a "Convert" button, rather than automatically detect a 1.0 card, please update the Walk-In flow to add a note that the APOS will return an error if a 2.0 card is tapped before a 1.0 card. Please include wireframes with this error in the FDR document. — Updated comment 01/03/22 (Balance Conversion PDR, Rev B, 12/17/21) — While this is addressed for the APOS walk-in case, please clarify the behavior for the laptop solution. Specifically, please clarify if the 2.0 credential info would auto-populate to the correct field, if an error would appear, or if it would populate in the 1.0 credential info field. — New comment 09/16/21 (Balance Conversion PDR, Rev A, 08/27/21) — Please clarify in the Balance Conversion CDRL what would occur if a CSA accidentally tapped an AFC 2.0 credential initially during conversion, instead of a 1.0 credential. Specifically, please clarify if the 2.0 credential info would auto-populate to the correct field, if an error would appear, or if it would populate in the 1.0 credential info field. | 2021-09-16 |  |  | Cubic - update submittal/prototype
7 | 0 | PMO | ⭐Balance conversion plan - generally | CDRL-OF-003-01.01 | Editorial changes to balance conversion CDRL | — Updated comment 11/18/22 (Balance Conversion, Rev D, 10/28/22) — Please consider whether the EMV details in Section 4.2 of the Balance Conversion CDRL better belong earlier in the document, such as in Section 3.2. Specifics about how EMV card numbers and Transit Account IDs will be handled at the mail-in solution can remain in Section 4.2, but the restriction on EMV is applicable to all Balance Conversion solutions. The CDRL should present a holistic overview of how EMV accounts will be rejected at each interface if such a card or Transit Account ID is presented for conversion. Separately, please correct the typo "Eligble" in the header of Section 2.1 ("Balances Eligble for Conversion") — New comment 06/17/22 (Balance Conversion PDR, Rev C, 05/27/22) — Some of the organization, sentence/paragraph/section structure, and terminology in the Balance Conversion PDR have made it difficult for MBTA stakeholders to gain a comprehensive understanding of the required outcomes and the solutions proposed for achieving those outcomes. The MBTA has redlined some suggested edits and restructuring aimed at addressing this concern. Please consider these suggestions in the development of the final design. The MBTA's redlines are available at: https://massdot.box.com/s/zkv0as31soy9vdews2f7jqecnrvaxx13 Relevant requirement 7.2 [...] Each stage in the design review process shall delve more deeply into detail to the point that both the MBTA and the SI have a comprehensive understanding of the required outcomes and the solutions proposed for achieving those outcomes. | 2022-06-17 |  |  | Cubic - address comment
8 | 0 | PMO | ⭐Balance conversion plan - generally | CDRL-OF-003-01.01 | Derived requirements for balance conversion | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — With the progression to Revised Final Design, please update the Compliance Matrix to incorporate the identified derived requirements. Please note any language changes that may be necessary upon considering comments logged against Rev D. — New comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Please update the Compliance Matrix to incorporate the following derived requirements related to the balance conversion solution: [Balance conversion transactions will appear in a User's purchase history on the System Website, Mobile App, IVR, CAT.] [The balance conversion solution] prevents "clone laundering" by preventing conversions of more than 2 conversions of AFC 1.0 cards that have the same card number. [...] The software will prevent AFC 1.0 cards with the same Card Number from being converted more than twice. If a AFC 1.0 Card Number is presented which has already been converted twice, a message will appear stating this information, the balance conversion process ends and will appear in the exceptions report. This report, delivered by Cubic, will allow MBTA the ability to run it as needed or have it scheduled to generate and distribute automatically daily or at a cadence of MBTA's choice. The following quantity of [balance conversion] devices will be provided, by Cubic, to the MBTA: • 25 APOS units at APOS locations • 4 Laptops at mobile sales unit • 5 Laptops for pop ups • 5 Laptop spares (to swap out units, not available for use generally but could be arranged by exception) • 5 Laptops at mail-in center = 44 devices in total. [The Balance Conversion] report will include information such as: Date/Time, Amount converted, Employee ID who performed the conversion, Cubic Device ID (which implies device type and location), AFC 1.0 card number, AFC 1.0 balance, AFC 1.0 card status, AFC 2.0 card number/Transit Account ID, AFC 2.0 Account balance after conversion, Order status, Conversion fee and funding source, Enablement fee and funding source, Total fees collected, and Address mailed to (if mail-in process was used). The balance conversion software will have the ability to read AFC 1.0 Media when presented via the TR4 and the Scheidt & Bachmann (S&B) API. ... When the card is presented the API call will return with the following possible card results: Hotlisted, Expired, Lost/Stolen, Passback, No valid product, or OK. Through the use of S&B’s Short IDs, the [Balance Conversion] software will be able to detect the presence of an AFC 1.0 pass ... The software will give a message to the CSA notifying the presence of a pass; instructing the CSA to abort the balance conversion process and instruct the User to return when the AFC 1.0 card no longer has an active/future pass. The AFC 2.0 system will prevent [balance] conversions that would result in a AFC 2.0 account exceeding the Configured AFC 2.0 account maximum. If, [during the balance conversion process], the User’s postal address was provided, [the SI shall] mail the AFC 1.0 card and the mail-in form back to the User with written confirmation stating the reason for the failed conversion. If the User did not have an existing Transit Account prior to the [mail-in balance] conversion, an AFC 2.0 card will be mailed to them with the contact information provided. If MBTA policy states so, the Enablement Fee will be automatically waived upon completing the balance conversion process. (Pending resolution of https://app.asana.com/0/767917605002993/1201647948336304/f) Note: Phrasing above differs from what appears in the document in order to correct the use of defined terms and to form requirements that stand on their own outside of the design document. Intent is the same as the design document. | 2022-06-13 |  |  | Cubic - address comment
9 | 0 | NV | ⭐Balance conversion plan - generally | CDRL-OF-003-01.01 | Account clarification window | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — While the MBTA now understands that users have 90 days to provide Cubic with any requested clarifications, there is no formal linkage in the document between the "90 Days to provide requested information" and the "Account clarification window." Please define this more explicitly. — New comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Please define "account clarification window," which is now only mentioned once in the Balance Conversion CDRL. | 2022-06-14 |  |  | Cubic - update submittal/prototype
10 | 0 | NV | ⭐Balance conversion plan - generally | CDRL-OF-003-01.01 | ConversionOrderUpdate notification | — Updated comment 11/19/22 (Balance Conversion, Rev D, 10/28/22) — In the template in Appendix D, please update the sentence "To view additional..." to the following: "You may view additional details about this conversion by logging in and viewing your purchase history at https://charlie.mbta.com/direct-link/purchase-history." Please also provide a screenshot of what this branded email would look like, using Charlie imagery, signatures, etc, in line with the System Website notifications. — New comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Please note, in the process outlined for each balance conversion method, that the ConversionOrderUpdate notification will always be sent to opted-in Registered Users upon a successful conversion. Consider also whether the email receipt option duplicates the functionality of this notification, and whether these can be consolidated somehow for users who have opted in to the notification. | 2022-06-14 |  |  | Cubic - update submittal/prototype
11 | 0 | JT, YK, NV | ⭐Balance conversion plan - additional content for final design | CDRL-OF-003-01.01 Section 2 | Sample balance conversion form | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — Please address the following changes to the balance conversion form: Make the form fields fillable so that a user can download the form, type into it and then print it out. This will improve legibility of submissions. Update the last sentence of the first paragraph to read: Please do not submit any CharlieTickets along with this form (including tappable and insertable versions). In the 7th paragraph, please add the word 'be' here: "Please note that a conversion fee may apply, and if so, will be deducted from the balance converted." — Updated comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Cubic has stated that a sample of this form will be provided in the Balance Conversion FDR CDRL. The MBTA looks forward to reviewing this sample when that CDRL is submitted. — Updated comment 01/03/22 (Balance Conversion PDR, Rev B, 12/17/21) — Cubic has stated that a sample of this form will be provided in the Balance Conversion FDR CDRL. The MBTA looks forward to reviewing this sample when that CDRL is submitted. — New comment 09/14/21 (Balance Conversion PDR, Rev A, 08/27/21) — Section 2 of the Balance Conversion CDRL states that a balance conversion form will need to be filled out for mailed requests. Please provide a sample of this form for review. Since Cubic will need an account identifier from users, the MBTA needs to ensure it is clear to users how to find either their credential number or Transit Account ID. | 2021-09-14 |  |  | Cubic - address comment
12 | 0 | YK | ⭐Balance conversion plan - additional content for final design | CDRL-OF-003-01.01 | Screen flows for Balance Conversion in FDR | — Updated comment 11/19/22 (Balance Conversion, Rev D, 10/28/22) — The MBTA has the following remaining feedback about the balance conversion screens: Please provide examples of what appears if the tooltip in screen 12A-2 and 12C-2 is selected. Please update the button using "AFC 2.0" in screen 12A-3 and 12C-3 to instead read "Next." Please update the typo in the "New Card Tapped" error message to state "A new card" instead of "An new card..." Please update the error messages to consistently use agent-centered language. For example, the "Balance Too High" alert should use language such as "Please instruct the customer to spend down..." This is especially important for the mail-in error messages. Please provide examples of what appears if the tooltips in screen 12A-4 are selected. Please change the capitalization of "barcode" in screen 12A.5.1. Please add a comma separator any time "Sorry" is used to start a message (i.e., "Sorry,"). Please update the "Charlie Card Not Active" error to add the word "by" between "Charlie App" and "visiting." Please remove the "New Card Media Read" heading on screen 12A-5 (in both the walk-in and mail-in flows). Please clarify at what point in the flow the agent would be redirected to upon selecting "Try again" in screen 12A-6.1 and 12C-5.1. Please change "Conversion Total" in screen 12A-7 and 12C-5 to "Updated New Card Balance." Please remove the "Valid" header from screen 12C-3 and 12A-3. Please clarify why clicking on the Mail-In Center link directs the MBTA to a page titled "12B Balance Conversion - Mobile Sales Unit." Please fix an apparent error in the mail-in flows wherein a "Balance Too High" error directs the agent to a screen about a failed barcode read. No barcodes will be read at the mail-in center. Please update the "Balances Too High" error in the mail-in flows to reflect the different procedures for the mail-in center. The agent's only option is to try to issue a new card or abort the process if insufficient contact details were provided. Please remove irrelevant errors from the mail-in flows. AFC 2.0 cards will never be tapped, scanned, etc. Please clarify what error message would appear if a 1.5 LUM was mistakenly tapped at any point in the flows. Please use "transit value" in lieu of "stored value" wherever "stored value" is used in order to align with AFC 2.0 terminology. — Updated comment 07/06/22 (APOS-P, Rev D, 06/24/22) — Please ensure all updated APOS with Payment flows include the "Balance Conversion" button once this is designed. — New comment 06/12/22 (Balance Conversion PDR, Rev C, 05/27/22) — During workshops it has been agreed upon that the SI will provide screen flows for the Balance Conversion software upon submission of the Final Design Document. Please ensure that this includes screens flows for both the APOS and laptop version. | 2022-06-16 |  |  | Cubic - address comment
13 | Transition CDR #11 | SWM | ⭐Balance conversion plan - additional content for final design | CDRL-OF-003-01.01.A | Sample of balance conversion receipt | — Updated comment 11/19/22 (Balance Conversion, Rev D, 10/28/22) — The MBTA has the following remaining feedback about the balance conversion receipt: Please align the card numbers in the conversion receipt. Currently, the new card number is shifted to the right. Please clarify the difference between "Total" and "Account Balance." These seem to be redundant and do not sufficiently describe what they are trying to. Consider changing "Total" to "Updated New Card Balance" and removing the "Balance" section. — Updated comment 05/31/22 (Balance Conversion PDR, Rev C, 05/27/22) — Cubic has stated that a sample of this form will be provided in the Balance Conversion FDR CDRL. The MBTA looks forward to reviewing this sample when that CDRL is submitted. — Updated comment 01/03/22 (Balance Conversion PDR, Rev B, 12/17/21) — The receipt sample provided in the Balance Conversion CDRL is not a relevant sample of an actual balance conversion. Rather, the sample provided is a receipt issued for repaying a negative balance. Please provide a relevant sample, as well as a receipt for the laptop solution. — Updated comment 09/14/21 (Balance Conversion PDR, Rev A, 08/27/21) — Please provide a sample of the balance conversion receipt we will provide to customers. — Original comment from 03/30/18 — Please provide a sample of the receipt that will be provided to Customers performing a balance conversion from AFC 1.0 to AFC 2.0. | 2018-03-30 |  |  | Cubic - update submittal/prototype
14 | Transition CDR #9 | SWM | ⭐Balance conversion plan - additional content for final design | PSR44-2.1; CDRL-OF-003-01.01.A | Converted balance appearance in AFC 2.0 system | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — The approach described in Cubic's 10/28/22 response and 10/24/22 Asana post sound acceptable, but are not documented in the design. please update the design to state how converted balance will appear in the user's purchase history, and add a derived requirement to the Compliance Matrix so that a test case can be mapped to it. — Updated comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Please update the Balance Conversion FDR submittal to show what conversion transaction looks like in a user's Purchase History. Please also clarify how the MBTA can rename this Back Office term. — Updated comment 01/11/22 (Balance Conversion PDR, Rev B, 12/17/21) — The response to this comment addressed back-end reporting but did not seem to address how these balances may be "differentiated in the customer's AFC 2.0 account to the customer." Please address this concern. — Updated comment 09/14/21 (Balance Conversion PDR, Rev A, 08/27/21) — Please describe, once an AFC 1.0 stored value balance is converted, how it is differentiated in the customer's AFC 2.0 account to the customer and any administrator reviewing the account. Specifically, please clarify if there will be a flag in the Cubic system to indicate that stored value on a user’s account came from a conversion. If users are allowed to bring in balance from multiple CharlieCards, please also clarify if any flag will indicate which card the balance came from. Related: — Original comment from 03/30/18 — Please describe how any balance converted from AFC 1.0 will be identifiable to the Customer and the Administrator through the Account Management Interfaces. | 2018-03-30 |  |  | Cubic - address comment
15 | 0 | NV | ⭐Balance conversion plan - additional content for final design | CDRL-OF-003-01.01 | FAQ samples for Balance Conversion support | — Updated comment 11/20/22 (Balance Conversion, Rev D, 10/28/22) — Please update Appendix C to align with the edits attached to this Asana task in v5 of the FAQs document. — New comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Please incorporate into the final design the content for the FAQs that will be used for Balance Conversion support, as mentioned in Section 4.5 of the CDRL. | 2022-06-16 |  |  | Cubic - update submittal/prototype
16 | 0 | SWM, AJV | ⭐Balance conversion plan - 1.0 and Interoperability | CDRL-OF-003-01.01 | Reliance on Interoperability for Balance Conversion | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — Thank you for adding language in Section 3.3 of the Balance Conversion Design to address the MBTA's concerns about reliance on the Interoperability Solution. Please consider the following edit to that sentence: If, for some reason, Cubic interoperability doesn’t progress in time for balance conversion or the interoperability solution is not able to meet the ARPA requirements for balance conversion, Cubic will engineer a different solution to allow balance conversion to progress. — Updated comment 06/17/22 (Balance Conversion PDR, Rev C, 05/27/22) — Although this topic has been discussed at length in workshops and many parts of it are addressed in the updated Balance Conversion CDRL, it has not been fully addressed by the Documentation provided to the MBTA. Balance conversion functionality is required to be available as early as Revenue Service Commencement and the availability of the Interoperability solution availability may not align with that same timeframe, and as of this writing, the Systems Integrator/Cubic has declined to enter into a Change Order to complete work on the Interoperability solution. The MBTA is particularly concerned that Cubic may not be considering appropriate sequencing of these activities based on the inaccurate dates listed in the 05/20/22 submission of the Compliance Matrix, as detailed further on "Balance conversion requirements deadline for first compliance is inconsistent", https://app.asana.com/0/0/1202342037477296). As to the technical solution, the short ticket_type_id is mentioned in the pass section, but is not mentioned in the "identifying the remaining SV" section. This could lead to confusion when identifying remaining Reduced Fare SV. There are different short ticket_type_ids for both identifying different types of passes and different types of Reduced Fare data. Note also that the pass data is stored in different sectors/blocks of the CharlieCard encoding than that of the stored value data. Please clearly describe how the Balance Conversion solution will be implemented differently in a world where Interoperability is and is not available at the ARPA's required timeframe. -- New comment 06/13/22 on Compliance Matrix (05/20/22) -- Please update the Compliance Matrix as needed to reflect the SI's intended approach to use the Interoperability solution to support balance conversion. — Original comment from 03/29/22 — Based on balance conversion preliminary design, Cubic intends to leverage Interoperability work to support balance conversion. Please provide more detail so that we can understand how this will work, including: These two areas of functionality are required to be available at different milestones. These two areas of functionality are required to be supported through different milestones. Balance conversion sites are unlikely to have Device IDs since no existing S&B device is at these locations. How cards which are not eligible to travel, but do have balance will be converted. Current S&B provided library may not provide sufficient information to support balance conversion. How the balance conversion team is coordinating with the interoperability team on this work. Approach for converting balance on AFC 1.0 media that has a pass on it (https://app.asana.com/0/0/836929767586042). How various edge cases that the MBTA has identified will be accounted for. What Cubic's expectations are for MBTA and S&B support of this approach. | 2022-03-29 |  |  | Cubic - address comment
17 | 0 | NV | ⭐Balance conversion plan - mail-in solution | CDRL-OF-003-01.01 | Sample communications for failed mail-in conversions | — Updated comment 11/20/22 (Balance Conversion, Rev D, 10/28/22) — If the issue with the conversion was a 2.0 account issue, and the user can likely fix the issue and reply to the Cubic email, please clarify if the conversion can continue without Cubic mailing the 1.0 card(s) back. If operationally feasible, please include a sample of an email communication that is sent in an effort to rectify 2.0 account issues before the card needs to be mailed back.. Both the core message and content in Table B-1 may need updating for the email version of this communication. Step 7c in the mail-in flow may need to be updated as well. Separately, please make the following content updates: When referring to old cards, if the term "Charlie Card" or "Charlie Ticket" is used, please use the compound "CharlieCard" or "CharlieTicket." In the error where an EMV account number was provided, please update the instructions to inform the user to either resubmit without an account number, or to get a new Charlie Card and provide those details instead. If they do not provide account details, a new account will be created for them. Please remove the duplicate entries for the old CharlieCard being hotlisted and disabled at the end of Table B-1. Please add a 1.0 error condition for the 1.0 balance being too high to convert. Please add a 1.0 error condition for when the serial number associated with the 1.0 card has already been converted twice. Please consider numbering the entries in Table B-1 for easier reference. — New comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — If form letter responses will be used for failed mail-in balance conversions (card hotlisted, user mailed a LUM, user submitted EMV credential info, etc), please provide drafts of these to the MBTA for review as part of the final design. Please include samples of both the letter that will be sent back with the 1.0 card and the email that will be sent if a return postal address was not provided. | 2022-06-14 |  |  | Cubic - update submittal/prototype
18 | 0 | NV | ⭐Balance conversion plan - mail-in solution | CDRL-OF-003-01.01 | Conversion to suspended and closed accounts | — Updated comment 11/18/22 (Balance Conversion, Rev D, 10/28/22) — In all instances where the design notes that 2.0 media must be returned to the user, please add "suspended due to negative balance" as an error condition. Please also update the wireframes to clarify where the flow would continue from after closing one of the 2.0-related error messages. — New comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — The mail-in center flows do not mention being unable to complete conversions for 2.0 Accounts in a Closed state (hotlisted, expired, etc.). Please clarify if any Back Office processes will block such conversions when such a 2.0 account/card number is input during a mail-in conversion. | 2022-06-14 |  |  | Cubic - update submittal/prototype
19 | 0 | NV | ⭐Balance conversion plan - mail-in solution | 0 | Packaging for balance conversion mailed cards | — Updated comment 11/18/22 (Balance Conversion, Rev D, 10/28/22) — Please add a CDRL reference to the Order Fulfillment CDRL for the balance conversion buck slip content and design. — New comment 09/15/22 (Implementation Plan, Order Fulfillment, Rev D, 08/26/22) — The MBTA did not receive a formal response to this item. Given that the balance conversion process includes extra material, such as instructions, the MBTA does not see how the fulfillment process described in this CDRL suits such cards. Please update the submittal to account for the extra material associated with balance conversion mail-ins. — New comment 07/25/22 (Order Fulfillment, Rev C, 06/03/22) — Please provide samples of the packaging that will be sent for fare cards mailed as part of the balance conversion mail-in process. | 2022-07-25 |  |  | Cubic - update submittal/prototype
20 | 0 | NV | ⭐Balance conversion plan - mail-in solution | CDRL-OF-003-02.01 | Accidental mailing of AFC 2.0 card | — New comment 11/19/22 (Balance Conversion, Rev D, 10/28/22) — Please clarify how the Cubic mail-in center would handle a scenario wherein a user accidentally mails in their AFC 2.0 card either 1) in lieu of their AFC 1.0 card(s) or 2) in addition to their AFC 1.0 card(s). | 2022-11-19 |  |  | Cubic - address comment
21 | 0 | PMO | ⭐Balance conversion plan - security and fraud | CDRL-OF-003-01.01.B | Infosec and CN consideration of conversion laptops | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — The updated Balance Conversion design refers to the Plan for Access Control for details, but that document has not be delivered to the MBTA. Related: "Plan for access control is past due" (https://app.asana.com/0/0/1202025180717956) — Updated comment 07/06/22 (Plan for Access Control, Rev C, 06/17/22) — The Plan for Access Control CDRL makes no mention whatsoever of the Balance Conversion solution. Please update this CDRL to align with the Balance Conversion documentation, making sure to align with both the MBTA's most recent comments and the InfoSec CDRL. — Updated comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — The MBTA has remaining questions about the login/authentication and access control procedures for Balance Conversion laptops. Of specific concern is the fact that the proposed approach conflicts with the general approach described in the accepted Information Security Plan prohibiting the use of generic logins. Please clarify what the "MBTA Workgroup" is that these laptops will be joined to, who manages these accounts, etc. If these details will be addressed in the Plan for Access Control, please state so explicitly. — New comment 01/11/22 (Balance Conversion PDR, Rev B, 12/17/21) — Please clarify what network and domain balance conversion laptops will be connected to, and if these laptops are accounted for in the CN and Infosec plans. | 2022-01-11 |  |  | Cubic - address comment
22 | 0 | Nafisah Nakhid, Policy | ⭐Balance conversion plan - security and fraud | 0 | AFC 1.0 card serial number and card type data in Cubic reports | — Updated comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — In recent Interoperability workshops, there has been discussion around a fare media type data being passed from S&B and stored in the Cubic system. Please update both Interoperability and Balance Conversion designs to add this field to reports. See related comment #2 in "Report on balance conversions sample" (https://app.asana.com/0/0/836929767586034). — New comment 10/27/22 (Interoperability) — Through the Interoperability 3 way workshops, we have identified a need for S&B to transmit card serial numbers and card type identifiers to Cubic for inspection and validation taps. Cubic needs to include this data - along with data that they are already reading about card type - in reports that are made available to the MBTA. Since card serial numbers are not unique across the card types, both fields are necessary to support accurate identification of cards for back office transaction reconciliation (https://app.asana.com/0/1165022983803697/1202239924838426/f). The following definitions have been identified for card type data: 7 = AFC 1.5 LUM - CharlieTicket 5 = AFC 1.0/1.5 MiFare Classic - CharlieCard These definitions should be explained in report documentation, but the card type IDs alone (i.e. 5 or 7) can be used in the reports. Please update the interoperability designs to reflect this. | 2022-10-27 |  |  | Cubic - address comment
23 | 0 | Policy, AFC 1.0 | ⭐Balance conversion plan - security and fraud | CDRL-OF-003-01.01.A | Duplicate CharlieCard serial numbers | — Updated comment 11/20/22 (Balance Conversion, Rev D, 10/28/22) — Please update the flows for "invalid 1.0 media" in the CDRL to note that if a duplicate serial number error appears, the balance conversion process ends. — Updated comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Please provide a wireframe of the alert that will appear when a 1.0 card number is attempted to be converted for the third+ time. — Updated comment 01/03/22 (Balance Conversion PDR, Rev B, 12/17/21) — Please update the CDRL to clearly state that the balance conversion processes will permit multiple AFC 1.0 cards all having the same serial number to be converted successfully. This will be manually monitored for potential fraud through reporting. — New comment 09/16/21 (Balance Conversion PDR, Rev A, 08/27/21) — The MBTA understands there to be a small number of CharlieCards with duplicate serial numbers. This will need to be considered in the Balance Conversion solution, as there appears to be a fraud check in place to prevent cards from being converted more than once. Related: https://app.asana.com/0/767917605002993/614482686912958 | 2021-09-16 |  |  | Cubic - address comment
24 | 0 | PMO | ⭐Balance conversion plan - security and fraud | CDRL-OF-003-01.01 | Report on balance conversions sample | — Updated comment 11/18/22 (Balance Conversion, Rev D, 10/28/22) — Please consider making the following updates to the Balance Conversion reports: Please consider changing the field name "Pre-AFC 1.0 Bal $" to simply "AFC 1.0 Bal $." Please separate the "5-" prefix that is part of the AFC 1.0 card serial number into its own field. There would therefore be two fields: "AFC 1.0 Card Prefix" and "AFC 1.0 Card Number" (as per https://app.asana.com/0/1165022983803697/1203252928029995/f). The "AFC 1.0 Card Prefix" field could alternatively be called "AFC 1.0 Card Type." Please use known card states in the "AFC 1.0 card status" and "AFC 2.0 TA Status" fields. These would include values such as Active, Suspended, Closed, etc. Please add an "N/A" value to the "Enablement Fee waived?" column, as this would be the more appropriate value if the conversion failed or did not involve the creation of a new 2.0 account. Rather than a "Mail-In Solution?" field, please consider whether it is possible to instead make this an "Employee Type" (Cubic/MBTA) field, and auto-fill "Cubic" if the device type was mail-in. Please consider parsing the "Device ID" field to add a column indicating the type of balance conversion location (mail-in, walk-in, MSU/pop-up). Separately, please update Section 2.4 of the CDRL to align the listed fields with those in the actual report. The MBTA also suggests renaming the "Exceptions" report to the "1.0 Duplicates" report. — Updated comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — Please provide samples of all Balance Conversion reports in the FDR submittal. — Updated comment 01/11/22 (Balance Conversion PDR, Rev B, 12/17/21) — The MBTA awaits delivery of FDR to review this report. At a minimum, MBTA Finance expects the following data fields to be populated for all conversion transactions: Old AFC 1.0 card number New AFC 2.0 card/account number Old AFC 1.0 Balance Conversion fee and funding source Enablement fee and funding source Total fees collected Total amount converted AFC 1.0 card status Note also that the CDRL reference to the Settlement & Liability Tracking document is a circular dead end. — Updated comment 09/14/21 (Balance Conversion PDR, Rev A, 08/27/21) — Please provide a sample of the Report on Balance Conversions so that the MBTA can confirm that it will support an internal need to close down any recurring activity on converted 1.0 media, Relevant requirement 4.4.5.1.7 The SI shall provide detailed accounting of all balance conversions. [CDRL: Report on balance conversions] [CDRL: Report on balance conversions ¦ Sample report] — Comment updated 11/29/18 to PSRs 44-2 and 44-2.1 — As discussed with Cubic, we don't expect that this would be a Cubic responsibility. Please reflect this in the balance conversion plan as a necessary step prior to balance conversion which the MBTA will be responsible for. -- Original comment -- The CSR needs to ensure that recurring loads established via the web site are disabled within the AFC 1.0 system prior to converting the balance. Please explain how the balance conversion plan will account for this. | 2018-09-25 |  |  | Cubic - address comment
25 | 0 | SWM | ⭐Balance conversion plan - security and fraud | CDRL-OF-003-02.01 | Use of historical AFC 1.0 Media sales data | — New comment 11/21/22 (Balance Conversion, Rev D, 10/28/22) — While earlier versions of the balance conversion design that were shared with the MBTA (e.g. https://app.asana.com/0/767917605002993/1200810996046783/f) accounted for looking up the AFC 1.0 card's historical data, the current version of the design doesn't account for this step as is required by 4.4.5.1.4. Please consider options for how data exports provided to Cubic by the MBTA from the S&B system can be used by the SI for secondary lookups to confirm card data (as a fallback method in the event that the interoperability solution is not able to meet the balance conversion requirements, and/or for fraud checks when reviewing balance conversion reports). Relevant requirement 4.4.5.1.4 The SI shall make use of historical AFC 1.0 Media sales data that may be provided by MBTA in its existing raw format to inform the conversion process and prevent fraud. | 2022-11-21 |  |  | Cubic - requires discussion
26 | 0 | 0 | ⭐Balance conversion plan - security and fraud | 0 | Requirement for use of historical AFC 1.0 Media sales data not being tracked correctly in the Compliance Matrix | — New comment 11/21/22 (Balance Conversion, Rev D, 10/28/22 and Compliance Matrix, 10/31/22) — The Compliance Matrix does not appear to be correctly tracking the requirement for the balance conversion solution to use historical AFC 1.0 Media sales data. It us a RDF1 value of "Use for Reference" and no values filled in for DDF, CDF, and MDF fields. Relevant requirement 4.4.5.1.4 The SI shall make use of historical AFC 1.0 Media sales data that may be provided by MBTA in its existing raw format to inform the conversion process and prevent fraud. | 2022-11-21 |  |  | Cubic - requires discussion
27 | 0 | Policy | ⭐Balance conversion plan - fees and configuration | CDRL-OF-003-01.01 | Error checking for exceeding balance limit | — Updated comment 11/19/22 (Balance Conversion, Rev D, 10/28/22) — While the design has been updated in accordance with the MBTA's previous comment, the steps described for each balance conversion interface do not reflect the new design. The wireframes instruct the agent to tell the user to spend down their balance or use a new card. The steps, however, still indicate that the user must restart the entire process. Please align the steps after a 2.0 card is tapped with the design, including the content of the error message. Further, please update Section 2 to remove the phrasing "... separate Transit Accounts will need to be created to carry any balance in excess of the allowed maximum." For accuracy, this could be changed to "If the combined (1.0 + 2.0) balance on an AFC 2.0 account would exceed the Configured AFC 2.0 Account maximum, a new Transit Account will need to be created to carry the balance from the 1.0 card." — Updated comment 06/22/22 (Balance Conversion PDR, Rev C, 05/27/22) — In the pop-up section, and wherever else applicable, it says the UI will instruct the User that the process must be restarted if the balance limit is breached. Please clarify if it is possible to allow a User to simply tap a new 2.0 card by selecting a "try another card" button or something similar, rather than start completely over. Further, now that the design has progressed to check whether adding the 1.0 balance to the 2.0 card would exceed the 2.0 balance limit and would not break the 1.0 balance across multiple Transit Accounts, please update Section 2 to reflect the design. Namely, please change the phrasing "... separate Transit Accounts will need to be created to carry any balance in excess of the allowed maximum." For accuracy, this could be changed to "... a new Transit Account will need to be created to carry the balance from the 1.0 card. The software solution will prompt the user when this needs to occur, as described in Section 4." — Updated comment 01/10/22 (Balance Conversion PDR, Rev B, 12/17/21) — Please clarify what error will be displayed to users to support the solution outlined in "Maximum 1.0 balance that can be converted" (https://app.asana.com/0/0/1200998834760265). CSAs should not be required to do math to determine if a card can proceed with conversion prior to submitting the conversion order. The System, ideally, should return an error, and inform the CSA that a new Transit Account must be created to convert the balance on the card in question. If this is not feasible, please clarify if the solution for lifting the balance cap (as designed for the FVM) can be leveraged here. — New comment 09/14/21 (Balance Conversion PDR, Rev A, 08/27/21) — Please describe error handling and user experience for the case when the available stored value on the AFC 1.0 CharlieCard, when added to the AFC 2.0 account balance, would exceed the maximum AFC 2.0 account balance ($500). | 2021-09-14 |  |  | Cubic - update submittal/prototype
Note on A10: Note: This column is to be used to provide each comment with a unique identification number.
Note on B10: MBTA: For tracking comments which have been submitted multiple times - either in other tracks or other stages. Export from Asana: Comment Tracking Field
Note on C10: MBTA: Export from Asana: MBTA Owner field
Note on D10: MBTA: Fill in from Asana: Section name -or- Use to separate multiple CDRLs being reviewed on one spreadsheet
Note on E10: MBTA: Export from Asana: Submittal ID Field
Note on F10: MBTA: Export from Asana: Task Name
Note on G10: MBTA: Export from Asana: Notes field